## Scope Summary
Category | Count | Meaning | MVP Treatment | Primary Basis | Client Action
Phase 1 UC List | 98 | Use cases currently scoped for the Phase 1 MVP implementation. | Included in Phase 1 MVP | UC List (P1), reflecting the latest client confirmations and accepted scope changes. | Confirm / implement Phase 1 scope
Phase 2 UC List | 61 | Use cases deferred from Phase 1 or planned for a later release. | Deferred to Phase 2 | UC List (P2), reflecting the latest phasing decisions and deferred capabilities. | Retain for Phase 2 planning
OOS / Not MVP | 5 | Use cases explicitly removed from the MVP scope. | Excluded from MVP | OOS - Not MVP sheet / confirmed scope exclusions. | Confirm exclusion
Pending Clarification | 0 | Use cases currently held pending a business clarification before final phasing. | Pending | Pending Clarification sheet. | Resolve open clarification

## UC List (P1)
UC ID | Use Case Name | Actor | Module/Feature | Portal | Description | WBS Reference | LTS suggestion | SGS Comments | ESt (Hour)
#REF!
1. Authentication | [8 empty] | 30
UC-AUTH-001 | Log In to Platform | All authenticated roles | Authentication | Customer Portal & SGS Portal | Authenticate with credentials and enter DTP with the role, tenant and affiliate context resolved for the session. | CP-01 User login & logout (P1) |  |  | 14
UC-AUTH-002 | Log Out of Platform | All authenticated roles | Authentication | Customer Portal & SGS Portal | Terminate the active session and invalidate the session token. | CP-01 User login & logout (P1) |  |  | 4
UC-AUTH-005 | Activate Account from Invitation | Customer Admin, Customer User, SGS User, SGS Consultant | Authentication | Customer Portal & SGS Portal | Accept a user invitation, set the initial password and complete first-time account activation. | CP-05 Create and manage customer users (P1); OPS-04 SGS customer onboarding (P1); Q&A #7; Q&A #59a |  |  | 12
2. User & Profile Management | [8 empty] | 40
UC-USR-001 | View User List | Customer Admin, SGS Admin | User Management | Customer Portal & SGS Portal | View the users within the permitted boundary (own tenant for Customer Admin; affiliate customers and SGS users for SGS Admin) with status and role. | CP-05 Create and manage customer users (P1); OPS-05 Customer and user administration (P1) |  |  | 8
UC-USR-002 | View User Details | Customer Admin, SGS Admin | User Management | Customer Portal & SGS Portal | View a user's profile, account status, assigned role and assigned scopes. | CP-05 Create and manage customer users (P1); OPS-05 Customer and user administration (P1) |  |  | 8
UC-USR-003 | Create User and Send Invitation | Customer Admin, SGS Admin | User Management | Customer Portal & SGS Portal | Create a user account, assign the initial role and issue an invitation. Includes resending or revoking a pending invitation. | CP-05 Create and manage customer users (P1); OPS-05 Customer and user administration (P1) |  |  | 10
UC-USR-005 | Assign Role to User | Customer Admin, SGS Admin | User Management | Customer Portal & SGS Portal | Assign or change the predefined platform role held by a user. Customer Admin manages customer-side roles; SGS Admin manages SGS-side roles, including the SGS Consultant role. | CP-05 Create and manage customer users (P1); OPS-05 Customer and user administration (P1); Q&A #59a |  |  | 8
UC-USR-006 | Assign Scope Access to Customer User | Customer Admin | User Management | Customer Portal | Grant a Customer User access to specific product, system or organizational scopes. | CP-05 Create and manage customer users (P1) |  |  | 6
3. Role & Permission Administration | [8 empty] | 43
UC-ROL-001 | Enforce Role, Tenant and Affiliate Permissions | System | Role & Permission | System / Backend (No Portal) | Enforce the predefined role and permission matrix on APIs and UI so customer users can access only their organization/scope data and SGS users, including SGS Consultants, can access only customers and functions permitted by their role and assignment boundary. | CP-03 User roles & permissions management (P1); Q&A #59a |  |  | 36
UC-ROL-002 | View Role Permission Matrix | Customer Admin, SGS Admin | Role & Permission | Customer Portal & SGS Portal | View the read/write/approve/share/admin permissions attached to a role, so administrators can choose the correct role when assigning users. | PRESALE WBS GAP — CP-03 (P1) 'Define permission matrix per PRD' is a design artefact, not a viewable matrix |  |  | 7
5. Notification | [8 empty] | 14
UC-NTF-001 | Generate In-App Notification | System | Notification | System / Backend (No Portal) | Generate role-, tenant- and scope-aware in-app notifications for relevant MVP events such as review feedback, service-request status changes and certification milestones. | CP-44 In-app notifications (P1); CP-28 Review notifications (P1); CP-35 Service request status flow & notification (P1); CP-42 Cert renewal/surveillance notifications (P1). Email notifications remain P2 under CP-45. |  |  | 8
UC-NTF-002 | View Notification Inbox and History | All authenticated roles | Notification | Customer Portal & SGS Portal | View current and historical notifications addressed to the user. | CP-44 |  |  | 6
6. Audit Trail | [8 empty] | 32
UC-AUD-001 | Record Audit Trail Entry | System | Audit Trail | System / Backend (No Portal) | Record append-only audit events for sensitive platform, review and service-request actions with actor, timestamp, action and affected object/context. | CP-47 Audit log (platform) (P1); OPS-17 Review audit log (P1); OPS-19 Service request audit log (P1) |  |  | 20
UC-AUD-002 | Search and View Audit Trail | SGS Admin | Audit Trail | SGS Portal | Search platform audit events by actor, object, action, date range and tenant for support, compliance and investigation. | CP-47 Audit log (platform) (P1) |  | Phase 2?
UC-AUD-004 | View Own Organization Activity Log | Customer Admin | Audit Trail | Customer Portal | Review activity performed on the organization's own evidence, certifications and users. | PRESALE WBS GAP — CP-47 (P1) is scoped to SGS Admin; no customer-facing activity log priced |  |  | 12
7. Framework Content Management | [8 empty] | 68
UC-FWK-001 | View Framework List | SGS Admin | Framework Content | SGS Portal | View the frameworks maintained on the platform and open their current framework content. | A5 Framework dynamic management (P1); OPS-07 Framework and cert configuration (P1) |  |  | 6
UC-FWK-002 | View Framework Details | SGS Admin | Framework Content | SGS Portal | View a framework's metadata, requirement/control structure and expected evidence types. Frameworks are managed independently in MVP; no ISO 27001/42001 cross-framework requirement/control equivalence mapping is included. | A5 Framework dynamic management (P1); OPS-07 Framework and cert configuration (P1); Q&A #18 cross-framework mapping OOS for MVP |  |  | 8
UC-FWK-003 | Create Framework | SGS Admin | Framework Content | SGS Portal | Register a new framework with its metadata and structural definition. | A5 Framework dynamic management (P1); OPS-07 Framework and cert configuration (P1) | move back to P1 | ISO27001, ISO42001 and CMS should be initially supported
UC-FWK-004 | Edit Framework Metadata | SGS Admin | Framework Content | SGS Portal | Modify framework-level metadata and structure supported by the framework data model. | A5 Framework dynamic management (P1); OPS-07 Framework and cert configuration (P1) |  |  | 8
UC-FWK-005 | Create Requirement or Control | SGS Admin | Framework Content | SGS Portal | Add a requirement or control to a framework, positioned within its clause hierarchy. | A5 Framework dynamic management (P1); OPS-07 Framework and cert configuration (P1) |  |  | 12
UC-FWK-007 | Retire Requirement or Control | SGS Admin | Framework Content | SGS Portal | Withdraw a requirement or control from future use while preserving existing customer evidence mappings. | PRESALE WBS GAP — Retirement preserving existing evidence mappings not priced; nearest A5 CRUD (P1), A8 migration (P2) |  |  | 8
UC-FWK-008 | Define Expected Evidence Types for a Control | SGS Admin | Framework Content | SGS Portal | Define the evidence types expected for a control and flag each as mandatory or optional. | A5 Framework dynamic management (P1) |  | What are the types of evidences? Files? This could be shifted to P2 | 8
UC-FWK-009 | Import Framework Content | SGS Admin | Framework Content | SGS Portal | Import or update SGS-supplied framework content from XLSX, including ISO 27001/42001 requirements/controls and expected evidence types, with each framework maintained independently. | OPS-07 Framework and cert configuration (P1); Q&A #16/#18 — XLSX input; ISO 27001/42001 cross-framework requirement/control mapping is OUT OF MVP |  |  | 18
UC-FWK-013 | Activate Framework | SGS Admin | Framework Content | SGS Portal | Make a framework version available for discovery, journeys and evidence workspaces. | PRESALE WBS GAP — Framework availability activation not priced; CP-12 (P1) is customer-side activation on a scope | move back to P1 | The framework needs to be available in P1, otherwise evidence management is useless! Or did I understand it wrong?
11. Customer Account Administration | [8 empty] | 40
UC-ACC-001 | View Customer Account List | SGS Admin, SGS User, SGS Consultant | Customer Account | SGS Portal | View customer accounts within the user's permitted SGS affiliate/assignment boundary. SGS Consultants see only customers assigned to them. | OPS-05 Customer and user administration (P1); Q&A #59f |  |  | 6
UC-ACC-002 | View Customer Account Details | SGS Admin, SGS User, SGS Consultant | Customer Account | SGS Portal | View a customer account's core profile, affiliate linkage, users and scopes within the permitted boundary. SGS Consultants are limited to their assigned customer. | OPS-05 Customer and user administration (P1); Q&A #59f |  |  | 5
UC-ACC-003 | Create Customer Account and Tenant | SGS Admin | Customer Account | SGS Portal | Create a customer account and its tenant as part of SGS customer onboarding. | OPS-04 SGS customer onboarding (P1) |  |  | 10
UC-ACC-004 | Edit Customer Account | SGS Admin | Customer Account | SGS Portal | Update SGS-maintained account attributes. | OPS-05 Customer and user administration (P1) |  |  | 5
UC-ACC-005 | Link Customer Account to SGS Affiliate | SGS Admin | Customer Account | SGS Portal | Assign the customer account to the owning SGS affiliate legal entity, which bounds all SGS-side visibility of that customer. | CP-03 User roles & permissions management (P1); OPS-05 Customer and user administration (P1) |  |  | 4
UC-ACC-006 | Assign SGS Personnel to Customer Account | SGS Admin | Customer Account | SGS Portal | Assign SGS personnel/owners to a customer account within the permitted affiliate boundary. For the SGS Consultant role, allow at most one active Consultant to be assigned to a customer. Automated conflict-of-interest checking is not part of MVP. | OPS-04 SGS customer onboarding (P1); Q&A #56 — automated COI controls removed from MVP; Q&A #59f — one Consultant per customer, assigned by SGS |  |  | 6
UC-ACC-007 | Invite Initial Customer Admin | SGS Admin | Customer Account | SGS Portal | Create and invite the first Customer Admin for a newly onboarded tenant. | OPS-04 SGS customer onboarding (P1); Q&A #7 |  |  | 4
13. Scope Management | [8 empty] | 36
UC-SCP-001 | View Scope List | Customer Admin, Customer User (+ SGS User, SGS Trainer/Assessor, SGS Auditor/Certification, SGS Consultant — assigned, read-only) | Scope Management | Customer Portal & SGS Portal | View the product, system and organizational scopes registered by the organization within the permitted customer/assignment boundary. | CP-06 Manage product/system/org scopes (P1); |  |  | 6
UC-SCP-002 | View Scope Details | Customer Admin, Customer User (+ assigned SGS roles including SGS Consultant, read-only) | Scope Management | Customer Portal & SGS Portal | View a scope's definition, obligation level, linked frameworks, workspaces, certifications and related context within the permitted assignment boundary. | CP-06 Manage product/system/org scopes (P1); |  |  | 5
UC-SCP-003 | Create Scope | Customer Admin | Scope Management | Customer Portal | Create an organization, product, or system scope. Organization and product are independent peer scopes; a system may belong to both an organization and a product. | CP-06 Manage product/system/org scopes (P1); Q&A #8 |  |  | 7
UC-SCP-004 | Edit Scope | Customer Admin | Scope Management | Customer Portal | Update an existing organization, product or system scope. | CP-06 Manage product/system/org scopes (P1); Q&A #8 |  |  | 5
UC-SCP-006 | Link Framework to Scope | Customer Admin | Scope Management | Customer Portal | Attach one or more frameworks to a scope, establishing the obligations to be prepared for and triggering workspace creation. | CP-06 Manage product/system/org scopes (P1) |  |  | 5
UC-SCP-007 | Unlink Framework from Scope | Customer Admin | Scope Management | Customer Portal | Withdraw a framework from a scope's active journey while retaining its evidence and review history. | PRESALE WBS GAP — Unlinking a framework from a scope is not priced |  |  | 8
14. Customer Cockpit | [8 empty] | 0
UC-CKP-001 | View Customer Cockpit | Customer Admin, Customer User, Customer Viewer | Customer Cockpit | Customer Portal | View the customer landing dashboard with Digital Trust status, pending actions and a recommended next step across the journey (discovery → training → advisory/readiness assessment → certification). | CP-07 Customer landing dashboard (P1); Q&A #10 | Phase 1 | Suggest to be included in P1
UC-CKP-002 | View Portfolio Matrix | Customer Admin, Customer User, Customer Viewer | Customer Cockpit | Customer Portal | View scopes against journey stages and frameworks in a matrix to compare progress across the portfolio. | CP-08 Journey Matrix view (P1) | Phase 1 | Suggest to be included in P1
17. Evidence Management | [8 empty] | 135
UC-EVD-001 | Create Evidence Workspace | Customer Admin, Customer User | Evidence Management | Customer Portal | Manually create an Evidence Workspace for a selected scope and framework for the current certification cycle. Only one workspace may exist for the same scope+framework within a certification cycle. | CP-13 Evidence workspace creation (P1); Q&A #19 |  |  | 8
UC-EVD-002 | Create Evidence Workspace on Framework Activation | System | Evidence Management | System / Backend (No Portal) | Automatically create the Evidence Workspace when a framework is activated on a scope, preventing duplicates for the same scope+framework in the current certification cycle. A new certification cycle creates a new workspace. | CP-13 Evidence workspace creation (P1); Q&A #19 |  |  | 5
UC-EVD-003 | View Evidence Workspace List | Customer Admin, Customer User | Evidence Management | Customer Portal | View and open the organization's Evidence Workspaces with their scope, framework and certification-cycle context. | CP-13 Evidence workspace creation (P1); Q&A #19 |  |  | 5
UC-EVD-004 | Browse Controls Catalogue | Customer Admin, Customer User | Evidence Management | Customer Portal | Browse the requirements and controls of the workspace's framework with their current evidence and declaration state. | CP-14 Controls catalogue browser (P1) |  |  | 9
UC-EVD-005 | View Control Details | Customer Admin, Customer User | Evidence Management | Customer Portal | View a control's text, expected evidence types, mapped evidence, maturity declaration and gap flags. | CP-14 Controls catalogue browser (P1) |  |  | 6
UC-EVD-006 | View Evidence Library | Customer Admin, Customer User | Evidence Management | Customer Portal | View all evidence held by the organization with metadata, mapping summary and status. | CP-15 Evidence library (P1) |  |  | 8
UC-EVD-007 | View Evidence Details | Customer Admin, Customer User | Evidence Management | Customer Portal | View an evidence item's stored file, metadata, mapped controls, freshness and current evidence/review status. | CP-15 Evidence library (P1) |  |  | 6
UC-EVD-008 | Upload Evidence | Customer Admin, Customer User | Evidence Management | Customer Portal | Upload an evidence file against one or more controls and capture supported metadata such as title, owner, description, version, dates, expiry/review date and comments. | CP-16 Upload evidence to control (P1); CP-49 Secure evidence document storage (P1); Q&A #54 |  |  | 16
UC-EVD-010 | Edit Evidence Metadata | Customer Admin, Customer User | Evidence Management | Customer Portal | Update an evidence item's metadata, including the dates that drive freshness. | CP-16 Upload evidence to control (P1); CP-15 Evidence library (P1) |  |  | 5
UC-EVD-011 | Map Evidence to Requirements or Controls | Customer Admin, Customer User | Evidence Management | Customer Portal | Manually map an existing evidence item to one or more requirements/controls selected by the user, including across frameworks where permitted. Updating shared evidence metadata/expiry applies to all linked controls; no automatic cross-framework control-equivalence mapping is included. | CP-16 Upload evidence to control (P1); Q&A #20; Q&A #18 — automatic ISO 27001/42001 cross-framework mapping is OUT OF MVP |  |  | 8
UC-EVD-012 | Remove Evidence Mapping | Customer Admin, Customer User | Evidence Management | Customer Portal | Remove a mapping between an evidence item and a control, with the completeness impact reflected. | CP-15 Evidence library (P1); CP-16 Upload evidence to control (P1) |  |  | 4
UC-EVD-013 | Replace Evidence with New Version | Customer Admin, Customer User | Evidence Management | Customer Portal | Supersede an evidence item with an updated version, retaining the prior version and its review history. | PRESALE WBS GAP — Evidence version supersession is not priced; CP-16 (P1) has 'version' as a metadata field only, not a version chain |  |  | 12
UC-EVD-014 | Update Evidence Workflow Status | Customer Admin, Customer User | Evidence Management | Customer Portal | Update evidence workflow status using the MVP status model defined in WBS (draft, submitted for review, reviewed, rejected, accepted or archived), subject to permitted transitions. | CP-20 Evidence workflow statuses (P1) |  |  | 8
UC-EVD-015 | Delete Evidence | Customer Admin | Evidence Management | Customer Portal | Permanently delete an evidence record and its stored file where retention policy permits, with the deletion recorded in the audit trail. | CP-15 Evidence library (P1); CP-47 Audit log (P1) |  |  | 5
UC-EVD-016 | Assign Requirement Owner | Customer Admin | Evidence Management | Customer Portal | Assign an internal owner to a requirement or control so preparation work and pending actions can be attributed. | Implicit — CP-17 'owner/comments' on the maturity declaration (P1) — requirement-level owner assignment not named |  |  | 5
UC-EVD-019 | Archive Evidence Workspace | Customer Admin | Evidence Management | Customer Portal | Close a workspace that is no longer active while retaining its evidence, declarations and review history. | PRESALE WBS GAP — Workspace closure not priced; CP-20 (P2) archives evidence and packages, not workspaces |  |  | 5
UC-EVD-020 | Access Assigned Customer Evidence | SGS Trainer/Assessor, SGS Auditor/Certification, SGS Consultant | Evidence Management | SGS Portal | Access the assigned customer's evidence and related requirement/control context within the permitted service/customer assignment. SGS Consultant access supports Implementation Support and Gap Analysis; customer evidence remains maintained through the existing Evidence Management workflow. | OPS-09 SGS scoped evidence access (P1); Q&A #56 — automated COI controls removed from MVP |  |  | 20
20. Training & SGS Academy | [8 empty] | 40
UC-TRN-001 | Browse SGS Academy Course Catalogue | Customer Admin, Customer User | SGS Academy | Customer Portal | Browse the Academy catalogue retrieved from the Academy API, with a graceful message where the catalogue is unavailable. | CP-29 Course catalogue integration (P1) |  |  | 20
UC-TRN-002 | View Course Details | Customer Admin, Customer User | SGS Academy | Customer Portal | View the course information returned by SGS Academy for a selected catalogue item. | CP-29 Course catalogue integration (P1) |  |  | 6
UC-TRN-009 | Browse On-site Training Catalogue | Customer Admin, Customer User | Training & SGS Academy | Customer Portal | View the catalogue of available on-site training services in DTP. DTP only displays/tracks on-site training for MVP and does not manage the actual training delivery. |  |  |  | 14
21. Service Request | [8 empty] | 81
UC-SRQ-001 | Submit Service Request | Customer Admin, Customer User | Service Request | Customer Portal | Submit a service request for an existing WBS-supported category, linked to the relevant scope/framework/certification. When launched from Evidence Management, pre-fill the scope, framework and evidence context. A Service Request may also be initiated from a Marketplace Consultant profile, in which case the customer-selected Consultant is carried into the Service Request. | CP-34 Submit service request (P1); A4 Service request trigger from Evidence Management (P1); Q&A #33 category detail still to confirm |  |  | 18
UC-SRQ-002 | View Service Request List | Customer Admin, Customer User, SGS User, SGS Trainer/Assessor, SGS Auditor/Certification, SGS Consultant | Service Request | Customer Portal & SGS Portal | View service requests within the permitted boundary: own organization for customers, assigned customers for SGS users, assigned activities for auditors, and consulting-related requests for the SGS Consultant's assigned customer. | CP-36 Service request listing (P1); OPS-18 Service request operations (P1) |  |  | 8
UC-SRQ-003 | View Service Request Details | Customer Admin, Customer User, SGS User, SGS Trainer/Assessor, SGS Auditor/Certification, SGS Consultant | Service Request | Customer Portal & SGS Portal | View a request's full content, linked scope and evidence, status history and customer-visible correspondence within the permitted boundary. SGS Consultants are limited to consulting-related requests for their assigned customer. | CP-35 Service request status flow & notification (P1); Q&A #59f/#59g |  |  | 8
UC-SRQ-004 | Cancel Service Request | Customer Admin, Customer User | Service Request | Customer Portal | Withdraw a submitted request that is no longer required, before SGS delivery begins. | PRESALE WBS GAP — Customer cancellation/withdrawal is not priced and is absent from the CP-35 status set (P1) |  |  | 4
UC-SRQ-005 | Triage Service Request | SGS User | Service Request | SGS Portal | Assess a submitted request and accept or reject it with a reason. | OPS-18 Service request operations (P1); CP-35 Service request status flow & notification (P1) |  |  | 8
UC-SRQ-006 | Assign Service Request | SGS Admin, SGS User | Service Request | SGS Portal | Assign or confirm the responsible SGS personnel for a Service Request based on the service type. For consulting requests, SGS may assign/confirm a Consultant, taking into account a customer-selected Consultant where applicable. For audit-related requests, SGS may assign the appropriate Auditor/Certification personnel. | OPS-18 Service request operations (P1); Q&A #34 manual assignment; Q&A #56 automated COI enforcement removed from MVP; Q&A #59f Consultant assignment by SGS |  |  | 10
UC-SRQ-007 | Update Service Request Status | SGS User, SGS Trainer/Assessor, SGS Auditor/Certification | Service Request | SGS Portal | Advance a request through its lifecycle to in progress or closed, triggering customer notification. | OPS-18 Service request operations (P1); CP-35 Service request status flow & notification (P1) |  |  | 8
UC-SRQ-008 | Add Internal Comment to Service Request | SGS User, SGS Trainer/Assessor, SGS Auditor/Certification | Service Request | SGS Portal | Record internal SGS notes that are not visible to the customer. | OPS-18 Service request operations (P1) |  |  | 5
UC-SRQ-009 | Request Information from Customer | SGS User, SGS Trainer/Assessor | Service Request | SGS Portal | Ask the customer for further information on a request and set it to information requested. | CP-35 Service request status flow & notification (P1); OPS-18 Service request operations (P1) |  |  | 6
UC-SRQ-010 | Respond to Information Request | Customer Admin, Customer User | Service Request | Customer Portal | Provide the requested information so the request can proceed. | PRESALE WBS GAP — No customer reply channel on a service request is priced; CP-25 (P1) is the review response, a different object |  |  | 6
22. Review Workflow | [8 empty] | 121
UC-REV-001 | Create Review | SGS User, SGS Trainer/Assessor, SGS Auditor/Certification | Review Workflow | SGS Portal | Create a review for the relevant customer, scope, framework, service request and evidence context. MVP supports exactly two review types — Readiness Assessment Review and Audit Review — and both are initiated by SGS; customers do not initiate reviews. | OPS-12 Create review (P1); A2 review-context separation (P1); Q&A #24/#25 |  |  | 12
UC-REV-002 | Assign Reviewer to Review | SGS Admin, SGS User | Review Workflow | SGS Portal | Assign the SGS person who will conduct the review. | PRESALE WBS GAP — Reviewer assignment is not priced; OPS-12 (P1) has no assignment bullet, CP-27 (P2) only displays assignment |  |  | 5
UC-REV-003 | View Review Queue | SGS User, SGS Trainer/Assessor, SGS Auditor/Certification | Review Workflow | SGS Portal | View assigned reviews with open items, items pending customer action and closed items. | CP-27 Review list & queues (P1) |  |  | 8
UC-REV-004 | View Review Details | SGS User, SGS Trainer/Assessor, SGS Auditor/Certification, Customer Admin, Customer User | Review Workflow | Customer Portal & SGS Portal | View review context, scope/framework, relevant evidence, comments, requests, requirement/control-level review statuses and the derived overall Review status, filtered to what each role is permitted to see. | OPS-13 SGS review evidence and controls (P1); CP-25 Customer review response (P1); Q&A #26 meeting confirmation |  |  | 12
UC-REV-005 | Update Requirement / Control Review Status | SGS Trainer/Assessor, SGS Auditor/Certification | Review Workflow | SGS Portal | Manually update the review status of each applicable Requirement/Criteria or Control within a Review. Different review items within the same Review may have different statuses at the same time. | CP-26 Review status per control (P1); Q&A #26 — client confirmed item-level status is manually updated by SGS |  |  | 10
UC-REV-006 | Add Review Comment | SGS Trainer/Assessor, SGS Auditor/Certification | Review Workflow | SGS Portal | Comment at evidence level or requirement level within the review thread. | OPS-13 SGS review evidence and controls (P1) |  |  | 6
UC-REV-007 | Request Clarification or Additional Evidence | SGS Trainer/Assessor, SGS Auditor/Certification | Review Workflow | SGS Portal | Raise a request to the customer for clarification or further evidence and set the item to await a response. | OPS-13 SGS review evidence and controls (P1); CP-26 Review status per control (P1) |  |  | 8
UC-REV-008 | Raise Finding | SGS Trainer/Assessor, SGS Auditor/Certification | Review Workflow | SGS Portal | Record a finding against a requirement, with its classification and the response required. | PRESALE WBS GAP — No finding object is priced; CP-25 (P1) prices the customer's response to findings that nothing creates |  |  | 16
UC-REV-011 | View Review Feedback | Customer Admin, Customer User | Review Workflow | Customer Portal | View SGS comments, clarification requests and findings for the user's assigned scope, labelled with the review context. | CP-25 Customer review response (P1) |  |  | 6
UC-REV-012 | Respond to Review Request | Customer Admin, Customer User | Review Workflow | Customer Portal | Respond to a comment or clarification request and attach or revise evidence. | CP-25 Customer review response (P1) |  |  | 8
UC-REV-013 | Submit Corrective Action | Customer Admin, Customer User | Review Workflow | Customer Portal | Submit a corrective action against a finding, with the action taken and its evidence. | CP-25 Customer review response (P1) |  |  | 8
UC-REV-014 | Evaluate Customer Response | SGS Trainer/Assessor, SGS Auditor/Certification | Review Workflow | SGS Portal | Evaluate a customer's clarification, revised evidence or corrective-action response and update the review item/status accordingly. | OPS-13 SGS review evidence and controls (P1); CP-26 Review status per control (P1) |  |  | 8
UC-REV-015 | Close Review | SGS Trainer/Assessor, SGS Auditor/Certification | Review Workflow | SGS Portal | Formally close a Review after all applicable Requirements/Criteria and Controls have been completed. Final closure is performed manually by an authorized SGS reviewer after the system-derived overall status indicates the review is ready for closure. | CP-26 Review status per control (P1); Q&A #26 — client confirmed manual item-level status, automatic overall roll-up and manual final Review closure by SGS |  |  | 6
UC-REV-016 | Derive Overall Review Status | System | Review Workflow | System / Backend (No Portal) | Automatically derive and update the overall Review status from the statuses of the applicable Requirements/Criteria and Controls within the Review. The derived status supports progress visibility and determines when the Review is eligible for final manual closure. | CP-26 Review status per control (P1); Q&A #26 — client confirmed automatic overall Review status roll-up |  |  | 8
23. Certification Record Management | [8 empty] | 22
UC-CRT-001 | Create Certification Record | SGS User | Certification Record | SGS Portal | Manually create a certification record for an assigned customer and scope/framework using the configured certification fields. | OPS-21 SGS cert record administration (P1); Q&A #36 manual SGS creation for MVP |  |  | 12
UC-CRT-003 | View Certification Record List | Customer Admin, Customer User, Customer Viewer, SGS User, SGS Admin | Certification Record | Customer Portal & SGS Portal | View certification records within the permitted boundary, with framework, scope, status and expiry. | CP-37 Certification listing (P1) |  |  | 10
25. Certification Maintenance | [8 empty] | 10
UC-CMT-002 | Generate Certification Milestone Notification | System | Certification Maintenance | System / Backend (No Portal) | Generate alerts for upcoming certification renewal or surveillance milestones and surface them through the MVP notification mechanism. | CP-42 Cert renewal/surveillance notifications (P1) | Phase 1 | Suggest to be included in P1 | 5
UC-CMT-007 | Generate Certification Milestone Notification | System | Certification Maintenance | System / Backend (No Portal) | Notify the customer and the assigned SGS user of approaching expiry, renewal and surveillance milestones, per the scheme's configured offsets. | Explicit — CP-42 Cert renewal/surveillance notifications — 'Scheduled jobs' (P1) | Phase 1 | Suggest to be included in P1 | 5
27. Operations Monitoring & Reporting | [8 empty] | 22
UC-OPS-001 | View SGS Operations Dashboard | SGS Admin, SGS User | Operations Monitoring | SGS Portal | View operational metrics within the affiliate and assignment boundary: active customers, open service requests, pending reviews, upcoming certification milestones, with drill-down to the underlying queues. | OPS-06 Admin overview dashboard (P1) | Phase 1 | Suggest to be included in P1 | 22
28. Consulting Services | [8 empty] | 22
UC-CNS-001 | Add Consulting Comment | SGS Consultant | Consulting Services | SGS Portal | Add customer-visible consulting comments within the assigned customer's requirement/control/evidence or gap context to support Implementation Support and Gap Analysis. MVP does not include structured recommendation/action-item tracking, consulting progress statuses or a system-generated final deliverable. | PRESALE WBS GAP — New customer-confirmed Consultant capability |  |  | 14
UC-CNS-002 | View Consulting Comments | Customer Admin, Customer User, SGS Consultant | Consulting Services | Customer Portal & SGS Portal | View consulting comments associated with the customer's compliance/evidence context. Customers may provide additional evidence through the existing Evidence Management flow, but MVP does not include chat or reply interaction on Consultant comments. | PRESALE WBS GAP — New customer-confirmed Consultant collaboration behavior |  |  | 8
29. DT Marketplace | [8 empty] | 78
UC-MKT-001 | View DT Marketplace | Customer Admin, Customer User | DT Marketplace | Customer Portal | View the DT Marketplace landing page and access the available Marketplace categories for MVP: Pentesting Services and Consultants. | NEW – Customer-confirmed Marketplace scope; Xavier confirmation 10-Sep-2026. Not included in presale WBS; add to task list for estimation. |  |  | 10
UC-MKT-002 | View Pentesting Service List | Customer Admin, Customer User | DT Marketplace | Customer Portal | View the list of available Pentesting Services provided in the Marketplace. MVP does not include search, filtering, booking or payment. | NEW – Customer-confirmed Marketplace scope; Pentesting list to be provided by SGS Taiwan team. Not included in presale WBS. |  |  | 10
UC-MKT-003 | View Pentesting Service Details | Customer Admin, Customer User | DT Marketplace | Customer Portal | View details of a selected Pentesting Service. For third-party Pentesting Services, DTP only displays the supplied service/provider information such as website, email and phone; no in-platform booking or payment is required. | NEW – Customer-confirmed Marketplace scope; Xavier clarification on third-party Pentesting Services. Not included in presale WBS. |  |  | 8
UC-MKT-004 | View Consultant Details | Customer Admin, Customer User | DT Marketplace | Customer Portal | View the list of Consultants available through the Marketplace. Each Consultant is represented as an individual profile rather than only as a generic consulting service. MVP does not include search or filtering. | NEW – Customer-confirmed Marketplace scope; Consultant list to be provided by SGS Taiwan team. Not included in presale WBS. |  |  | 10
UC-MKT-005 | Customer Admin, Customer User | Customer Admin, Customer User | DT Marketplace | Customer Portal | View the profile and details of a selected Consultant. From the Consultant detail view, the customer can proceed to the existing Submit Service Request flow with that Consultant selected. | NEW – Customer-confirmed Marketplace scope; Xavier confirmed individual Consultant profiles and customer selection of a specific Consultant. Not included in presale WBS. |  |  | 12
UC-MKT-006 | Manage Marketplace Content | SGS Admin | DT Marketplace | SGS Portal | Create, update, activate/deactivate and remove Marketplace content for Pentesting Services and Consultant profiles. Marketplace content is maintained by SGS Admin. | NEW – Customer-confirmed Marketplace administration; Xavier confirmed content is maintained by SGS Admin. Not included in presale WBS; requires estimation. |  |  | 28
30. Statement of Applicability | [8 empty] | 0
UC-SOA-001 | Manage Statement of Applicability | Customer Admin, Customer User | Statement of Applicability | Customer Portal | Define and maintain whether each requirement/control is applicable or not applicable for a selected Scope and Framework, including the justification for exclusions.
UC-SOA-002 | View Statement of Applicability | Customer Admin, Customer User, SGS Admin, SGS Auditor, SGS Consultant (View Only) | Statement of Applicability | Customer Portal & SGS Portal | View the Statement of Applicability for a selected Scope and Framework, including each requirement/control's applicability status and the justification for controls marked as not applicable.

## UC List (P2)
UC ID | Use Case Name | Actor | Module/Feature | Portal | Description | WBS Reference | LTS suggestion | SGS Comments | ESt (Hour)
#REF!
1. Authentication | [8 empty] | 0
UC-AUTH-003 | Request Password Reset | All authenticated roles | Authentication | Customer Portal & SGS Portal | Request a password reset link when the password cannot be recalled, and set a new password from that link. | Implicit — CP-01 (P1) — self-service password reset not named; only auth API, password policy, session timeout | Phase 2 | Ok. In case reset is needed, team can support the client
UC-AUTH-004 | Change Own Password | All authenticated roles | Authentication | Customer Portal & SGS Portal | Change the current password while authenticated, subject to the SGS password policy. | Implicit — CP-01 (P1) — change-password not named | Phase 2 | Ok. In case reset is needed, team can support the client
2. User & Profile Management | [8 empty] | 0
UC-USR-004 | Edit User Account | Customer Admin, SGS Admin | User Management | Customer Portal & SGS Portal | Update another user's account attributes maintained by an administrator. | CP-05 Create and manage customer users (P1); OPS-05 Customer and user administration (P1) | Phase 2
UC-USR-007 | Activate User Account | Customer Admin, SGS Admin | User Management | Customer Portal & SGS Portal | Re-enable a previously deactivated user account. | Implicit — OPS-05 'Reset/disable access' (P1) — re-activation not named | Phase 2
UC-USR-008 | Deactivate User Account | Customer Admin, SGS Admin | User Management | Customer Portal & SGS Portal | Disable a user's access while retaining the user record and its history. | OPS-05 Customer and user administration (P1) | Phase 2
UC-USR-009 | Delete User Account | Customer Admin, SGS Admin | User Management | Customer Portal & SGS Portal |  | CP-05 Create and manage customer users (P1); OPS-05 Customer and user administration (P1) | Phase 2
UC-USR-010 | Reset User Password | Customer Admin, SGS Admin | User Management | Customer Portal & SGS Portal | Trigger the administrator password-reset flow for another user without exposing the new password to the administrator; a temporary password is issued to the account owner, who must change it on first login. | OPS-05 Customer and user administration (P1); Q&A #45 | Phase 2
3. Role & Permission Administration | [8 empty] | 0
UC-ROL-003 | Create Role | SGS Admin | Role & Permission | SGS Portal | Define a new role and select its permission set. | PRESALE WBS GAP — No role authoring in the estimation; FRD assumption 4.3 fixes a 7-role RBAC model | Phase 2
UC-ROL-004 | Edit Role Permissions | SGS Admin | Role & Permission | SGS Portal | Modify the permission set of a custom role. | PRESALE WBS GAP — No permission authoring in the estimation; FRD assumption 4.3 fixes a 7-role RBAC model | Phase 2
UC-ROL-005 | Delete Role | SGS Admin | Role & Permission | SGS Portal | Remove a custom role that is no longer assigned to any user. | PRESALE WBS GAP — No role authoring in the estimation; FRD assumption 4.3 fixes a 7-role RBAC model | Phase 2
5. Notification | [8 empty] | 0
UC-NTF-003 | Manage Notification Templates and Events | SGS Admin | Notification | SGS Portal | Maintain notification templates and the mapping of platform events to templates and recipient rules. | OPS-23 Platform notifications admin (P1) | Phase 2
7. Framework Content Management | [8 empty] | 0
UC-FWK-006 | Edit Requirement or Control | SGS Admin | Framework Content | SGS Portal | Modify the text, hierarchy position, applicability level or attributes of a requirement or control. | A5 Framework dynamic management (P1); OPS-07 Framework and cert configuration (P1) | Phase 2
UC-FWK-014 | Deactivate Framework | SGS Admin | Framework Content | SGS Portal | Withdraw a framework from new use while preserving all historical usage and records. | PRESALE WBS GAP — Framework deactivation not priced; nearest OPS-07 admin config (P2) | Phase 2
8. Certification Configuration | [8 empty] | 0
UC-SCH-001 | View Certification Scheme List | SGS Admin | Certification Scheme | SGS Portal | View the certification schemes configured on the platform. | Implicit — OPS-07 cert configuration (P2) — no certification scheme entity is named | Phase 2
UC-SCH-002 | View Certification Scheme Details | SGS Admin | Certification Scheme | SGS Portal | View a scheme's record structure, permitted statuses, sharing rules and maintenance cycle configuration. | Implicit — OPS-07 (P2) — no certification scheme entity is named | Phase 2
UC-SCH-003 | Create Certification Scheme | SGS Admin | Certification Scheme | SGS Portal | Define a new certification scheme linked to a framework, so certification records can be raised against it. | PRESALE WBS GAP — No certification scheme object in the estimation; OPS-07 (P2) configures fields on records only | Phase 2
UC-SCH-004 | Configure Certification Record Fields and Statuses | SGS Admin | Certification Scheme | SGS Portal | Configure the fields captured on certification records and the permitted certification status values. | OPS-07 Framework and cert configuration (P1); CP-39 Certification lifecycle statuses (P1) | Phase 2
UC-SCH-005 | Configure Certification Sharing Rules | SGS Admin | Certification Scheme | SGS Portal | Configure the certification sharing rules supported by the platform. | OPS-07 Framework and cert configuration (P1) | Phase 2
UC-SCH-006 | Configure Surveillance and Renewal Cycle Rules | SGS Admin | Certification Scheme | SGS Portal | Define the surveillance interval, renewal lead time and milestone notification offsets for a scheme. | PRESALE WBS GAP — Surveillance interval / renewal lead-time configuration not priced; CP-42 (P1) prices the alerts but not the rules | Phase 2
UC-SCH-007 | Activate Certification Scheme | SGS Admin | Certification Scheme | SGS Portal | Make a scheme available for new certification records. | PRESALE WBS GAP — No scheme lifecycle in the estimation | Phase 2
UC-SCH-008 | Deactivate Certification Scheme | SGS Admin | Certification Scheme | SGS Portal | Withdraw a scheme from new use while preserving issued certification records. | PRESALE WBS GAP — No scheme lifecycle in the estimation | Phase 2
10. Platform & Tenant Configuration | [8 empty] | 0
UC-CFG-001 | Configure Platform Settings | SGS Admin | Platform Configuration | SGS Portal | Configure platform-level settings and per-tenant feature toggles so SGS can enable or disable supported modules without a release. | B3 Platform configuration + feature toggles (P1) | Phase 2
UC-CFG-002 | Configure Default Evidence Freshness Rules | SGS Admin | Platform Configuration | SGS Portal | Define default freshness periods by framework or evidence type, applied where evidence carries no expiry or review date. | PRESALE WBS GAP — Default freshness rules by framework/evidence type (PRD RL-07) not priced; CP-16 (P1) uses evidence dates only | Phase 2
11. Customer Account Administration | [8 empty] | 0
UC-ACC-008 | Activate Customer Account | SGS Admin | Customer Account | SGS Portal | Activate an account so its users may access the platform. | OPS-04 SGS customer onboarding (P1) | Phase 2
UC-ACC-009 | Suspend Customer Account | SGS Admin | Customer Account | SGS Portal | Suspend platform access for an account while retaining all data. | Implicit — OPS-04 tenant activation status (P1); OPS-05 'disable access' (P1) | Phase 2
UC-ACC-010 | Offboard Customer Account | SGS Admin | Customer Account | SGS Portal | Close an account and apply the agreed retention, deletion or anonymisation treatment to its data. | PRESALE WBS GAP — Offboarding with retention / deletion / anonymisation (PRD NFR-PRV-03/04) not priced | Phase 2
12. Organization Profile Management | [8 empty] | 0
UC-ORG-001 | View Organization Profile | Customer Admin, Customer User | Organization Profile | Customer Portal | View the organization's own profile as held on the platform. | CP-04 Organization profile management (P1) | Phase 2
UC-ORG-002 | Edit Organization Profile | Customer Admin | Organization Profile | Customer Portal | Maintain the organization's profile information supported by the platform. | CP-04 Organization profile management (P1) | Phase 2
13. Scope Management | [8 empty] | 0
UC-SCP-005 | Archive Scope | Customer Admin | Scope Management | Customer Portal | Retire a scope from active use while retaining its historical records. | PRESALE WBS GAP — Archive/retire preserving history not priced; CP-06 CRUD (P1) implies hard delete only | Phase 2
UC-SCP-008 | Define Obligation Coverage Between Scopes | Customer Admin | Scope Management | Customer Portal | Record that an organization-level scope, control or certification supports one or more product- or system-level obligations. | A1 Organization-level to product/system-level obligation linkage (P1) | Phase 2
14. Customer Cockpit | [8 empty] | 0
UC-CKP-003 | View Assigned Customer Cockpit | SGS User, SGS Trainer/Assessor, SGS Auditor/Certification, SGS Consultant | SGS Cockpit | SGS Portal | View the trimmed cockpit for an assigned customer, showing only information permitted for the role's customer assignment and access permissions. | PRESALE WBS GAP — Trimmed SGS Assessor/Auditor cockpit (PRD CC-16, NFR-UX-02); Q&A #59a/#59f extends assigned-customer access to SGS Consultant | Phase 2
15. Customer Journey | [8 empty] | 0
UC-JRN-001 | View Journey for a Scope | Customer Admin, Customer User, Customer Viewer (+ assigned SGS roles, read-only) | Customer Journey | Customer Portal | View the Discovery → Training → Gap Analysis → Assessment → Audit → Certification journey for a scope, with per-stage status, pending items and entry points into the responsible module. | CP-09 Journey view (linear stages) (P1) | Phase 2
UC-JRN-002 | View Framework-Specific Journey Progress | Customer Admin, Customer User, Customer Viewer | Customer Journey | Customer Portal | View journey progress separately per framework where a scope carries several frameworks. | CP-09 Journey view (linear stages) (P1) | Phase 2
UC-JRN-003 | View Obligation Coverage Relationship | Customer Admin, Customer User | Customer Journey | Customer Portal | See where an organization-level control, framework or certification satisfies a product- or system-level obligation. | A1 Organization-level to product/system-level obligation linkage (P1) | Phase 2
UC-JRN-004 | Derive Journey Stage Status | System | Customer Journey | System / Backend (No Portal) | Derive each stage's status from readiness, review, service request and certification state, and mark stages not started, in progress, completed, blocked or not applicable. | Implicit — CP-09 'Stage status labels' (P1) — the derivation rules per stage are not itemised | Phase 2
18. Self-Assessment & Maturity Declaration | [8 empty] | 0
UC-ASM-001 | Declare Control Maturity | Customer Admin, Customer User | Self-Assessment | Customer Portal | Declare control maturity as implemented, partial, not implemented or N/A and capture the owner/comments supported by the WBS. | CP-17 Maturity self-declaration (P1) | Phase 2
UC-ASM-002 | Update Maturity Declaration | Customer Admin, Customer User | Self-Assessment | Customer Portal | Update the customer's maturity declaration for a control, including status, owner and comments. | CP-17 Maturity self-declaration (P1) | Phase 2
UC-ASM-003 | View Self-Assessment Summary | Customer Admin, Customer User (+ assigned SGS roles, read-only) | Self-Assessment | Customer Portal | View the distribution of maturity declarations across a framework or scope and the requirements still undeclared. | Implicit — CP-23 'Surface maturity self-declaration' (P1) — no dedicated self-assessment summary view | Phase 2
19. Readiness Indicators | [8 empty] | 0
UC-RDN-001 | Calculate Readiness Indicators | System | Readiness Indicators | System / Backend (No Portal) | Calculate evidence completeness and freshness and roll them up with maturity declarations, rule-based gaps and review states at the applicable scope/framework level. | CP-23 View readiness indicators (P1) | Phase 2
UC-RDN-002 | Evaluate Rule-Based Gap Indicators | System | Readiness Indicators | System / Backend (No Portal) | Apply deterministic MVP gap rules such as implemented without evidence, outdated evidence and missing maturity declaration, and explain each flag. | CP-18 Rule-based gap indicators (P1) | Phase 2
UC-RDN-003 | Detect Outdated Evidence | System | Readiness Indicators | System / Backend (No Portal) | Flag evidence as outdated when its expiry or review date drives a freshness issue and surface the result in readiness indicators. | CP-16 Upload evidence to control (P1); CP-23 View readiness indicators (P1) | Phase 2
UC-RDN-004 | View Readiness Indicators | Customer Admin, Customer User, Customer Viewer (+ assigned SGS roles including SGS Consultant, read-only) | Readiness Indicators | Customer Portal & SGS Portal | View a centralized readiness overview within Evidence Management for the selected scope/framework, including completeness, freshness, declared maturity, gap and review indicators, with drill-down to contributing requirements and evidence. | CP-23 View readiness indicators (P1); Q&A #23 — client confirmed centralized readiness overview integrated in Evidence Management | Phase 2
UC-RDN-005 | View Gap List | Customer Admin, Customer User, SGS Consultant (assigned, read-only) | Readiness Indicators | Customer Portal & SGS Portal | View the open rule-based gaps for a scope or framework with the explanation of the triggering condition. Assigned SGS Consultants may use this view to support Gap Analysis without creating separate structured gap-status or action-item records. | CP-18 Rule-based gap indicators (P1) | Phase 2
20. Training & SGS Academy | [8 empty] | 0
UC-TRN-004 | Proceed to SGS Academy for Enrolment | Customer Admin, Customer User | SGS Academy | Customer Portal | Hand off to SGS Academy for enrolment, cart and payment, which remain owned by Academy. | CP-31 Redirect to Academy for enrolment (P1) | Phase 2
UC-TRN-005 | Retrieve Training Badges from Academy | System | SGS Academy | System / Backend (No Portal) | Retrieve completed-course badge information from the Academy API and associate each badge with the corresponding user profile. | CP-32 Training badges display (P1) | Phase 2
UC-TRN-006 | View Training Badges | rket | SGS Academy | Customer Portal | View completed-course training badges on the dedicated badges/profile view, clearly distinguished from certifications. | CP-32 Training badges display (P1) | Phase 2
UC-TRN-008 | Link Badge to User Profile | Customer Admin | SGS Academy | Customer Portal | Allow badges to be linked to the user profile and, where appropriate, to the customer organization training/capability view. | Explicit — CP-32 'Profile badges page' (P1) — organization capability view not named | Phase 2
23. Certification Record Management | [8 empty] | 0
UC-CRT-002 | Edit Certification Record | SGS User | Certification Record | SGS Portal | Update permitted certification record fields, with every change captured in the audit trail. | OPS-21 SGS cert record administration (P1) | Phase 2
25. Certification Maintenance | [8 empty] | 0
UC-CMT-001 | Update Certification Lifecycle Status | SGS Admin, SGS User | Certification Maintenance | SGS Portal | Update the certification lifecycle status using the MVP statuses defined in WBS, including active, surveillance, pending renewal, suspended, withdrawn and expired, with SGS-controlled transitions. | CP-39 Certification lifecycle statuses (P1); Q&A #38 confirms recurrence differs by standard (no additional recurrence feature added beyond current WBS) | Phase 2
UC-CMT-003 | Suspend Certification | SGS Auditor/Certification | Certification Maintenance | SGS Portal | Suspend a certification, with reason and effective date, and reflect the suspension in internal and shared views. | Explicit — CP-39 'suspended' + 'Transitions by SGS' (P1) | Phase 2
UC-CMT-004 | Withdraw Certification | SGS Auditor/Certification | Certification Maintenance | SGS Portal | Withdraw a certification permanently, with reason and effective date, and revoke any external sharing of it. | Explicit — CP-39 'withdrawn' + 'Transitions by SGS' (P1) | Phase 2
UC-CMT-005 | Expire Certification | System | Certification Maintenance | System / Backend (No Portal) | Set a certification to expired when its validity period ends without renewal. | Explicit — CP-39 'expired' (P1) — automatic expiry job not named | Phase 2
UC-CMT-006 | Reinstate Certification | SGS Auditor/Certification | Certification Maintenance | SGS Portal | Return a suspended or expired certification to active status with the basis recorded. | Implicit — CP-39 'Transitions by SGS' (P1) — reinstatement is not among the named transitions | Phase 2
26. Digital Trust Passport & External Sharing | [8 empty] | 0
UC-PSP-001 | View Digital Trust Passport | Customer Admin, Customer User, Customer Viewer | Digital Trust Passport | Customer Portal | View the customer's Digital Trust Passport / trust view showing certification information and other approved current trust information supported by the Phase 1 WBS. | CP-37 Certification listing (P1) | Phase 2
UC-PSP-002 | Configure Certification Visibility | Customer Admin | Digital Trust Passport | Customer Portal | Decide which certifications are visible internally and which may be shared externally. | CP-40 Internal/external visibility controls (P1); Q&A #39 detail still to confirm | Phase 2
UC-PSP-003 | Select Trust Information for Sharing | Customer Admin | Digital Trust Passport | Customer Portal | Select which supported trust information is visible internally or externally, according to the configured visibility controls. | CP-40 Internal/external visibility controls (P1) | Phase 2
UC-PSP-004 | Generate Shareable Trust Profile Link | Customer Admin | Digital Trust Passport | Customer Portal | Generate a tokenized, read-only trust-profile link for external stakeholders, with expiry/revocation supported by the WBS. DTP login is not required for the recipient. | CP-41 Shareable trust profile link (P1); Q&A #40/#41 | Phase 2
UC-PSP-005 | View Shared Trust Profile | External Stakeholder | Digital Trust Passport | External Shared View (No Portal) | View approved certification and trust information through a valid external share link without a DTP login, subject to link validity and the configured sharing controls. | CP-41 Shareable trust profile link (P1); Q&A #40 | Phase 2
UC-PSP-007 | View Trust Profile Access Log | Customer Admin | Digital Trust Passport | Customer Portal | View when and by whom a shared trust profile was accessed. | PRESALE WBS GAP — No customer-facing share access log is priced; CP-47 (P1) logs sharing actions for SGS Admin only | Phase 2
27. Operations Monitoring & Reporting | [8 empty] | 0
UC-OPS-002 | Monitor Assigned Customer Journeys | SGS User | Operations Monitoring | SGS Portal | Monitor journey stage and readiness progress across assigned customers to identify where SGS engagement is needed. | CP-09 Journey view (P1); OPS-06 Admin overview dashboard (P1) | Phase 2
UC-OPS-003 | Monitor Integration Health | SGS Admin | Operations Monitoring | SGS Portal | Review integration failures and degraded-mode events exposed by the platform so operational intervention can be taken where required. | CP-50 Integration error handling (P1) | Phase 2

## Future Release
UC ID | Use Case Name | Actor | Module/Feature | Description | WBS Reference | Reason for Future Release | Portal
1. Authentication
UC-AUTH-006 | Authenticate via Enterprise SSO | All authenticated roles | Authentication | Authenticate through a customer or SGS enterprise identity provider, with roles derived from IdP claims. | Explicit — CP-02 Enterprise SSO readiness (P2 — adapter stub only) | Enterprise SSO is explicitly Phase 2 / readiness only, not part of the MVP user flow. | Customer Portal & SGS Portal
7. Framework Content Management
UC-FWK-010 | Publish Framework Version | SGS Admin | Framework Content | Publish a new version of a framework, making it available to new journeys while leaving in-flight journeys on their existing version. | Explicit — A8 'Version history retained' (P2) | Framework version publishing is Phase 2 (A8). | SGS Portal
UC-FWK-011 | Migrate Evidence Mappings to New Framework Version | SGS Admin, System | Framework Content | Re-map existing customer evidence and maturity declarations onto a new framework version, reporting items that require manual re-mapping. | Explicit — A8 'Version migration and re-mapping of existing evidence' (P2) | Framework version migration and evidence re-mapping are Phase 2 (A8). | SGS Portal
9. Regulatory Discovery Configuration
UC-DCF-001 | View Question List | SGS Admin | Discovery Configuration | View the discovery question bank with type, status and usage. | Implicit — OPS-07 'Configure Regulatory Discovery questions/logic (RD-14)' (P2) — one bullet covers the whole question bank | Regulatory Discovery configuration is deferred from the first pilot; Q&A #12–14 mark the approach as low priority / to be decided. | SGS Portal
UC-DCF-002 | View Question Details | SGS Admin | Discovery Configuration | View a question's full configuration, including answer options and the rules that consume it. | Implicit — OPS-07 RD questions/logic bullet (P2) | Regulatory Discovery configuration is deferred from the first pilot; Q&A #12–14. | SGS Portal
UC-DCF-003 | Create Question and Answer Options | SGS Admin | Discovery Configuration | Create a discovery question with its answer options and input constraints. | Implicit — OPS-07 RD questions/logic bullet (P2) | Regulatory Discovery configuration is deferred from the first pilot; Q&A #12–14. | SGS Portal
UC-DCF-004 | Edit Question | SGS Admin | Discovery Configuration | Modify a question's wording, options or constraints. | Implicit — OPS-07 RD questions/logic bullet (P2) | Regulatory Discovery configuration is deferred from the first pilot; Q&A #12–14. | SGS Portal
UC-DCF-005 | Archive Question | SGS Admin | Discovery Configuration | Withdraw an obsolete question from future questionnaires while retaining historical responses. | Implicit — OPS-07 RD questions/logic bullet (P2) | Regulatory Discovery configuration is deferred from the first pilot; Q&A #12–14. | SGS Portal
UC-DCF-006 | View Questionnaire List | SGS Admin | Discovery Configuration | View the configured discovery questionnaires with version and status. | Implicit — OPS-07 RD questions/logic bullet (P2) — questionnaire as an object is not named | Regulatory Discovery configuration is deferred from the first pilot; Q&A #12–14. | SGS Portal
UC-DCF-007 | View Questionnaire Details | SGS Admin | Discovery Configuration | View a questionnaire's question composition, ordering and branching. | Implicit — OPS-07 RD questions/logic bullet (P2) | Regulatory Discovery configuration is deferred from the first pilot; Q&A #12–14. | SGS Portal
UC-DCF-008 | Create Discovery Questionnaire | SGS Admin | Discovery Configuration | Assemble questions into an ordered questionnaire for a defined discovery purpose. | Implicit — OPS-07 RD questions/logic bullet (P2) | Regulatory Discovery configuration is deferred from the first pilot; Q&A #12–14. | SGS Portal
UC-DCF-009 | Edit Discovery Questionnaire | SGS Admin | Discovery Configuration | Modify a questionnaire's composition, ordering or branching logic. | Implicit — OPS-07 RD questions/logic bullet (P2) | Regulatory Discovery configuration is deferred from the first pilot; Q&A #12–14. | SGS Portal
UC-DCF-010 | Archive Discovery Questionnaire | SGS Admin | Discovery Configuration | Withdraw an obsolete questionnaire while retaining completed discovery records. | Implicit — OPS-07 RD questions/logic bullet (P2) | Regulatory Discovery configuration is deferred from the first pilot; Q&A #12–14. | SGS Portal
UC-DCF-011 | Import Applicability Rule Set | SGS Admin | Discovery Configuration | Import an SGS-supplied applicability rule file, with validation and an import result report. | Explicit — CP-11 'Import SGS rules content' (P1) | Applicability rule-set administration belongs to Regulatory Discovery, which Q&A #12–14 defer from the first pilot. | SGS Portal
UC-DCF-012 | View Applicability Rule List | SGS Admin | Discovery Configuration | View the rules that map answer combinations to recommended frameworks and obligation levels. | Implicit — OPS-07 RD questions/logic bullet (P2) — rule set is not inspectable in any priced UI | Regulatory Discovery rule administration is deferred from the first pilot; Q&A #12–14. | SGS Portal
UC-DCF-013 | Create or Edit Applicability Rule | SGS Admin | Discovery Configuration | Maintain an individual rule linking answer conditions to recommended frameworks, obligation level and next actions. | Implicit — OPS-07 RD questions/logic bullet (P2) | Regulatory Discovery rule administration is deferred from the first pilot; Q&A #12–14. | SGS Portal
UC-DCF-014 | Maintain Recommendation Explanation Text | SGS Admin | Discovery Configuration | Maintain the explanation shown to the customer for why a framework may apply, plus the mandatory indicative-only disclaimer. | Implicit — CP-11 'Explain each recommendation' (P1) renders it; authoring falls under OPS-07 (P2) | Recommendation content authoring belongs to deferred Regulatory Discovery configuration; Q&A #12–14. | SGS Portal
UC-DCF-015 | Configure Recommended Next Actions | SGS Admin | Discovery Configuration | Configure which next actions a discovery outcome offers, such as start a readiness workspace, view training or submit a service request. | Implicit — CP-12 (P1) implements the runtime next steps; configuring them falls under OPS-07 (P2) | Discovery next-action configuration belongs to the deferred Regulatory Discovery approach; Q&A #12–14. | SGS Portal
16. Regulatory Discovery
UC-RGF-001 | View and Manage Regulatory Feed | Customer Admin, Customer User | Regulatory Discovery | Customer Portal | View applicable regulatory-feed items, filter them by sector, geography and date, and mark items as read. | Regulatory feed function in WBS (originally P2); Q&A #58 confirms inclusion in Phase 1
UC-DSC-001 | Complete and Submit Discovery Questionnaire | Customer Admin, Customer User | Regulatory Discovery | Start a discovery for an organization, product or system, answer the guided intake covering organization type, sector, geography, market and scope type, and submit it for evaluation. Saving and resuming a partial questionnaire is an alternate flow. | Explicit — CP-10 Guided intake questionnaire (P1), incl. 'Save draft' | Customer Regulatory Discovery intake is not part of the first pilot per Q&A #12–14; keep for a later release after the approach is agreed. | Customer Portal
UC-DSC-002 | Generate Applicability Result | System | Regulatory Discovery | Evaluate submitted answers against the published rule set and produce recommended frameworks classified by obligation level, each with its explanation. | Explicit — CP-11 'Rules engine execution' (P1) | Applicability evaluation is deferred with Regulatory Discovery per Q&A #12–14. | System / Backend (No Portal)
UC-DSC-003 | View Discovery Result | Customer Admin, Customer User | Regulatory Discovery | Review the recommended frameworks, the rationale for each, the obligation level and the indicative-only disclaimer. | Explicit — CP-11 'display results to UI' + 'Explain each recommendation' (P1) | Discovery result presentation is deferred with Regulatory Discovery per Q&A #12–14. | Customer Portal
UC-DSC-004 | Create or Update Scope from Discovery Result | Customer Admin | Regulatory Discovery | Create a new scope or update an existing one from the discovery outcome. | Explicit — CP-12 'create product/system/org scope' (P1) | Creating/updating scope from discovery is deferred with Regulatory Discovery per Q&A #12–14. | Customer Portal
UC-DSC-005 | Activate Recommended Frameworks | Customer Admin | Regulatory Discovery | Select which recommended frameworks to activate on a scope. | Explicit — CP-12 Activate frameworks on journey (P1) | Activating recommended frameworks from discovery is deferred with Regulatory Discovery per Q&A #12–14. | Customer Portal
17. Evidence Management
UC-EVD-009 | Bulk Upload Evidence | Customer Admin | Evidence Management | Upload multiple evidence files and apply or edit metadata in bulk as an asynchronous job. | Explicit — CP-21 Bulk upload and bulk metadata edit (P2, Low priority) | Bulk evidence upload/edit is Phase 2 and low priority (CP-21). | Customer Portal
UC-EVD-017 | Create Evidence Package | Customer Admin, Customer User | Evidence Management | Create and maintain a separate Evidence Package containing the evidence/documents to be submitted for a Readiness Assessment or Audit Review. | Explicit — CP-19 'Package builder UI' (P2) | Q&A #21 now confirms Evidence Package is a separate system object (Option A). Implementation remains Future Release because CP-19 places the package builder in Phase 2. | Customer Portal
UC-EVD-018 | Submit Evidence Package for Review | Customer Admin | Evidence Management | Submit the separate Evidence Package to SGS for review, moving it into the submitted state and linking it to the applicable Review. | Explicit — CP-19 'Submit package status' + 'Link to Review Workflow' (P2); A4 evidence-to-service-request handoff (P1) | Q&A #21 confirms the separate Evidence Package concept; package submission remains Future Release because CP-19 is Phase 2. | Customer Portal
19. Readiness Indicators
UC-RDN-006 | Create Readiness Snapshot | System | Readiness Indicators | Persist a periodic readiness snapshot per scope and framework so that trends can be reported. | Explicit — A3 'Periodic readiness snapshots' (P2) | Periodic readiness snapshots are Phase 2 (A3). | System / Backend (No Portal)
UC-RDN-007 | View Readiness Trend | Customer Admin, Customer User (+ assigned SGS roles, read-only) | Readiness Indicators | View improvement or deterioration in completeness and freshness over time for a scope and framework. | Explicit — A3 'Trend chart per scope and framework' + 'Surface on the Passport view' (P2) | Readiness trend visualization is Phase 2 (A3). | Customer Portal
UC-RDN-008 | Export Readiness Report | Customer Admin, Customer User, SGS User | Readiness Indicators | Export readiness and evidence status, with the preparation-metric disclaimer applied and subject to role and tenant permissions. | Explicit — CP-22 Export evidence/readiness report (P2); CP-24 Readiness reports (P2) | Readiness/evidence report export is Phase 2 (CP-22/CP-24). | Customer Portal & SGS Portal
20. Training & SGS Academy
UC-TRN-003 | View Recommended Training | Customer Admin, Customer User | SGS Academy | View courses recommended for the scope's active frameworks and identified readiness gaps. | Explicit — CP-30 Framework-linked course recommendations (P2) | Framework-linked training recommendations are Phase 2 (CP-30). | Customer Portal
UC-TRN-007 | Approve Training Badge for Trust Profile | Customer Admin | SGS Academy | Approve which badges may appear on the Digital Trust Passport and shared trust profile. | Explicit — CP-33 Optional badges on Passport (P2) | Selecting training badges for Passport display is Phase 2 (CP-33). | Customer Portal
22. Review Workflow
UC-REV-009 | Accept Evidence Package | SGS Trainer/Assessor, SGS Auditor/Certification | Review Workflow | Accept a submitted evidence package as meeting the applicable review criteria. | Implicit — CP-20 'accepted' state (P2); CP-19 package submission (P2) — no explicit reviewer accept action | Evidence Package acceptance depends on the Phase 2 package workflow (CP-19/CP-20). Q&A #21 has clarified the package concept; timing remains Future Release. | SGS Portal
UC-REV-010 | Reject Evidence Package | SGS Trainer/Assessor, SGS Auditor/Certification | Review Workflow | Reject a submitted package with reasons and the actions required from the customer. | Implicit — CP-20 'rejected' state (P2) — no explicit reviewer reject action | Evidence Package rejection depends on the Phase 2 package workflow (CP-20). Q&A #21 has clarified the package concept; timing remains Future Release. | SGS Portal
23. Certification Record Management
UC-CRT-004 | View Certification Record Details | Customer Admin, Customer User, Customer Viewer, SGS User, SGS Admin | Certification Record | View a record's full detail, attached certificate documents, surveillance and renewal milestones, and its history of previous certificates, renewals and status changes. | Explicit — CP-38 Certification details and history (P2) | Certification details/history is Phase 2 (CP-38). | Customer Portal & SGS Portal
UC-CRT-005 | Upload Certificate Document | SGS User | Certification Record | Attach the issued certificate document to a record in secure storage, marked as SGS-verified. | Explicit — A9 Upload certificate (P2); CP-49 secure document storage (P1) | Certificate document upload is Phase 2 capability (A9); secure storage alone being P1 does not make the business UC MVP. | SGS Portal
UC-CRT-006 | Register Customer-Provided Certification | Customer Admin | Certification Record | Record a certification the organization holds from SGS or a third party outside DTP, stored as customer-provided information and visually distinguished from SGS-verified records. | Explicit — A9 Upload certificate — 'customer-uploaded cert documents' (P2) | Customer-provided certification registration is Phase 2 (A9). | Customer Portal
UC-CRT-007 | Set Trust Information Provenance | System, SGS User | Certification Record | Assign and carry the provenance of every trust record — SGS-verified, SGS assessment, customer-provided, third-party or automated signal — through display, sharing and export. | Explicit — A9 'Provenance attribute on trust records' + 'Provenance badge' + 'carried through export' (P2) | Trust-information provenance model/badging is Phase 2 (A9). | SGS Portal
UC-CRT-008 | View Certification Reporting | SGS Admin | Certification Record | Report on certification records by type, status, expiry, scope, geography and customer account. | Explicit — OPS-22 Cert reporting (P2, Low priority) | Certification reporting is Phase 2 / low priority (OPS-22). | SGS Portal
26. Digital Trust Passport & External Sharing
UC-PSP-006 | Verify Shared Trust Information | External Stakeholder | Digital Trust Passport | Verify the authenticity of shared certification and trust information through the platform's verification mechanism. | Explicit — CP-43 Share verification (advanced) (P2, Low priority) | Advanced share verification is Phase 2 / low priority (CP-43). | External Shared View (No Portal)

## OOS - Not MVP
UC ID | Use Case Name | Actor | Module/Feature | Description | WBS Reference | Reason for OOS / Not MVP | Portal
4. Impartiality & Conflict-of-Interest Control
UC-COI-001 | Evaluate Conflict of Interest on Assignment | System | Impartiality Control | Cross-check a proposed assignment of an SGS person to a customer scope against service requests, prior readiness reviews, assessment activity, audit activity, certification activity and evidence review history, then block or flag it per the configured rules. | Explicit — CP-48 'COI rule engine' (P1); OPS-09 'COI checks before grant' (P1); OPS-18 'enforce COI rules' (P1) | Explicitly removed from the MVP by customer confirmation Q&A #56 ('Let's remove from MVP scope, not critical at this stage'). Q&A #47 also states COI is not really required for the MVP. | System / Backend (No Portal)
UC-COI-002 | Override Conflict-of-Interest Warning | SGS Admin | Impartiality Control | Record a justified override of a flagged (non-blocking) conflict, capturing the reason and approver. | Explicit — CP-48 'Log checks/overrides' (P1) | Explicitly removed from the MVP together with COI controls by customer confirmation Q&A #56. | SGS Portal
UC-COI-003 | Configure Conflict-of-Interest Rules | SGS Admin | Impartiality Control | Maintain the rule set that determines which role and service combinations are incompatible on the same customer scope. | Implicit — CP-48 rule engine (P1) — no rule configuration UI priced; PRD NFR-MNT-03 says 'where feasible' | Explicitly removed from the MVP together with COI controls by customer confirmation Q&A #56. | SGS Portal
UC-COI-004 | View Conflict-of-Interest Check History | SGS Admin | Impartiality Control | Review past conflict checks, warnings, overrides and assignment decisions for accreditation and internal audit purposes. | Implicit — CP-48 'Log checks/overrides' (P1) + CP-47 Audit Log UI (P1) — no dedicated COI history view | Explicitly removed from the MVP together with COI controls by customer confirmation Q&A #56. | SGS Portal
7. Framework Content Management
UC-FWK-012 | Map Controls Across Frameworks | SGS Admin | Framework Content | Maintain equivalence mappings between controls of different frameworks so that shared evidence and shared controls can be recognised. | NOT DEFINED — Cross-framework control equivalence mapping is not priced anywhere | Explicitly OUT OF MVP by customer confirmation Q&A #18: ISO 27001 / ISO 42001 requirement cross-mapping is excluded from the MVP. | SGS Portal

## Pending Clarification
UC ID | Use Case Name | Actor | Module/Feature | Description | WBS Reference | Portal
No pending clarification use cases currently tracked